## Hasan Husseini
To-do list
To be completed by: |  |  |  | Name: Hasan Husseini
Deadline: |  |  |  | Date: 11/23/25
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-11-21 | 2025-11-21 |  | <1
100% | Prepare DB, research relevant topics | 2025-11-21 | 2025-11-22 |  | <1
100% | Prepare To-Do List | 2025-11-22 | 2025-11-23 |  | 1
100% | Create UDTs | 2025-11-24 | 2025-11-26 | 2025-11-28 | 1
100% | Design normalized tables in accordance with UDTs | 2025-11-26 | 2025-11-28 | 2025-11-29 | 1
100% | Create full group ERD | 2025-11-28 | 2025-11-29 |  | 1
100% | Fill allotted Powerpoint slides | 2025-11-28 | 2025-11-29 |  | <1
100% | Group Recording | 2025-11-29 | 2025-11-29 |  | <1
100% | Submit | 2025-11-30 | 2025-11-30 |  | <1

## Micheal Cipriani
To-do list
To be completed by: |  |  |  | Name Micheal Cipriani
Deadline: |  |  |  | Date 11/30/25
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-11-21 | 2025-11-21 |  | <1
100% | Prepare DB, research relevant topics | 2025-11-21 | 2025-11-22 |  | <1
100% | Prepare To-Do List | 2025-11-22 | 2025-11-23 |  | 1
100% | Create UDTs | 2025-11-24 | 2025-11-26 |  | 1
100% | Design normalized tables in accordance with UDTs | 2025-11-26 | 2025-11-28 |  | 1
100% | Create full group ERD | 2025-11-28 | 2025-11-29 |  | 1
100% | Fill allotted Powerpoint slides | 2025-11-28 | 2025-11-29 |  | <1
100% | Group Recording | 2025-11-29 | 2025-11-29 |  | <1
100% | Submit | 2025-11-30 | 2025-11-30 |  | <1

## Youlun Wang
To-do list
To be completed by: |  |  |  | Youlun Wang
Deadline: |  |  |  | Due Date: 11/30/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-11-21 | 2025-11-21 |  | <1
100% | Prepare DB, research relevant topics | 2025-11-21 | 2025-11-22 |  | <1
100% | Prepare To-Do List | 2025-11-22 | 2025-11-23 |  | 1
100% | Create UDTs | 2025-11-24 | 2025-11-26 |  | 1
100% | Design normalized tables in accordance with UDTs | 2025-11-26 | 2025-11-28 |  | 1
100% | Create full group ERD | 2025-11-28 | 2025-11-29 |  | 1
100% | Fill allotted Powerpoint slides | 2025-11-28 | 2025-11-29 |  | <1
100% | Group Recording | 2025-11-29 | 2025-11-29 |  | <1
100% | Submit | 2025-11-30 | 2025-11-30 |  | <1

## Giorgos Stefanis
To-do list
To be completed by: |  |  |  | Name Giorgos SStefanis
Deadline: |  |  |  | Date 11/28/25
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-11-21 | 2025-11-21 |  | <1
100% | Prepare DB, research relevant topics | 2025-11-21 | 2025-11-22 |  | <1
100% | Prepare To-Do List | 2025-11-22 | 2025-11-23 |  | 1
100% | Create UDTs | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2
100% | Design normalized tables in accordance with UDTs | 2025-11-25 | 2025-11-26 |  | 1
100% | Create full group ERD | 2025-11-28 | 2025-11-29 |  | 1
100% | Fill allotted Powerpoint slides | 2025-11-28 | 2025-11-29 |  | <1
100% | Group Recording | 2025-11-29 | 2025-11-29 |  | <1
100% | Submit | 2025-11-30 | 2025-11-30 |  | <1

## Seeram Govindan
To-do list
To be completed by: |  |  |  | Name Seeram Govindan
Deadline: |  |  |  | Date 11/29/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-11-21 | 2025-11-21 |  | <1
100% | Prepare DB, research relevant topics | 2025-11-21 | 2025-11-22 |  | <1
100% | Prepare To-Do List | 2025-11-22 | 2025-11-23 |  | 1
100% | Create UDTs | 2025-11-24 | 2025-11-26 |  | 1
100% | Design normalized tables in accordance with UDTs | 2025-11-26 | 2025-11-28 |  | 1
100% | Create full group ERD | 2025-11-28 | 2025-11-29 |  | 1
100% | Fill allotted Powerpoint slides | 2025-11-28 | 2025-11-29 |  | <1
100% | Group Recording | 2025-11-29 | 2025-11-29 |  | <1
100% | Submit | 2025-11-30 | 2025-11-30 |  | <1

## Ridhwan Ibrahim
To-do list
To be completed by: |  |  |  | Name Ridhwan Ibrahim
Deadline: |  |  |  | Date 11/29/25
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-11-21 | 2025-11-21 |  | <1
100% | Prepare DB, research relevant topics | 2025-11-21 | 2025-11-22 |  | <1
100% | Prepare To-Do List | 2025-11-22 | 2025-11-23 |  | 1
100% | Create UDTs | 2025-11-24 | 2025-11-26 |  | 1
100% | Design normalized tables in accordance with UDTs | 2025-11-26 | 2025-11-28 |  | 1
100% | Create full group ERD | 2025-11-28 | 2025-11-29 |  | 1
100% | Fill allotted Powerpoint slides | 2025-11-28 | 2025-11-29 |  | <1
100% | Group Recording | 2025-11-29 | 2025-11-29 |  | <1
100% | Submit | 2025-11-30 | 2025-11-30 |  | <1